## Slide 1: 2024 Loudoun ARES Simulated Emergency Test (SET) Plan
Event Date: 5 October 2024

## Slide 2: Background
Background:
  Amateur Radio Emergency Service (ARES) consists of licensed amateurs who have voluntarily registered their qualifications and equipment, with their local ARES leadership, for communications duty in the public service when disaster strikes (from ARRL)
    includes training, preparation, organization, and guidelines
  The Simulated Emergency Test (SET) is one of the ARRL activities to exercise/practice emergency communications (EMCOMM)
    usually in early October
    Is conducted nation-wide and at the local level
    Is scenario based

## Slide 3: Purpose & Scope
Purpose of the Loudoun ARES SET for 2024: To initiate Loudoun ARES activities for EMCOMM training and to exercise a draft comm plan
Scope: Conducted within Loudoun County using the Loudoun Emergency Operations Center (EMOC) to:
  Coordinate a limited number of fixed and mobile ham stations for the transfer of simulated emergency messages (similar to LARG support for bike events)
  Use linked repeater assets – for start of exercise
  Include a simulated fail over period to exercise simplex communications
  Include testing of WinLink to transfer email and standard forms
  May or may not include connections to EMCOMM interfaces outside of the county such as the National Traffic System (NTS)

## Slide 4: Scenario (adapted from the Virginia ARES 2024 SET Plan)
Type of Emergency: This exercise will use the scenario of a Virginia-wide winter storm, with some widespread power outages, many smaller localized outages, and reduced transportation due to snow, ice, downed trees, flooding, etc.
Loudoun ARES (LARES) is asked to provide auxiliary communications for Loudoun County emergency services organizations for set up and operation of shelters, warming stations, food distribution facilities including Loudoun Inova Hospital’s support for the simulated emergency

## Slide 5: Planned Stations/Positions (TBR) (1 of 2) (note: all stations run APRS for location tracking)
Loudoun Inova Hospital supported by a portable station (two operators?)
  VHF/UHF for in-county comms to Loudoun Emergency Operations Center and shelters as needed
  Possibly set up in remote area of hospital parking lot – need to coordinate
  Traffic to handle:
    number of injured, medical care needed, supplies needed
    Both voice and Winlink
4 shelters supported by portable fixed stations
  VHF/UHF for in-county comms to net control
  HF for NTS welfare messages?
  Set up at various parks in the county to simulate shelter locations
  Traffic to handle:
    number of injured, medical care needed, supplies needed
    welfare messages to relatives (both in and out of county?)
    Both voice and Winlink
  Adjust number of stations depending on number of volunteers

## Slide 6: Planned Stations/Positions (TBR) (2 of 2) (note: all stations run APRS for location tracking)
4 mobile stations
  VHF/UHF for in-county comms – voice coms
  Rovers to report status of various things such as bridges, power stations, road conditions around the county, and to transport supplies as dispatched by Net Control
  Adjust number of stations depending on number of volunteers
2 operator positions at Loudoun Emergency Operations Center
  Net control on primary operation net (in-county comms)
  Execute MSEL
  External interface to Red Cross, Loudoun Inova Hospital, and other supported agencies
  Traffic to handle:
    Primary interface with county emergency personnel
    number of injured, medical care needed, supplies needed
    welfare messages to relatives (both in and out of county?)
    Dispatch mobile stations
    Both voice and Winlink

## Slide 7: Candidate Simulated Loudoun County Shelter Locations (in work)
Leesburg - Ida Lee Park?
Ashburn/Brambleton
Purcellville/Hamilton
Lovettsville
South Riding
Philomont
Middleburg
Sterling
Question – what would be the most probable locations in real life with accessable areas (& restroom facilities)?

## Slide 8: INCIDENT RADIO COMMUNICATIONS PLAN (ICS 205) - DRAFT
Zone Grp. | Ch # | Function | Channel Name/Trunked Radio System Talkgroup | Assignment | RX Freq N or W | RX Tone/NAC | TX Freq N or W | TX Tone/NAC | Mode (A, D, or M) | Remarks | 
A | 1 | Primary Net Control (linked to A Group) | LOUDOUN ARES WB6EFW VHF FM | Loudoun EOC | 145.185- | 103.5 Hz | – 0.6 MHz | 103.5 Hz | FM Voice | Repeater located at Inova Hospital Lansdown | 
A | 2 | Primary Net Control (linked to A Group) | LOUDOUN ARES - WB6EFW UHF | Loudoun EOC | 442.1375+ | need to check | + 5.0 MHz | need to check | FM Voice | Repeater located at Inova Hospital Lansdown | 
A | 3 | Primary Net Control (linked to A Group) | BLUEMONT N3JLT | Loudoun EOC | 147.300+ | 146.2 Hz | + 0.6 MHz | 146.2 Hz | FM Voice | Repeater located at Bluemont, VA (use is TBD) | 
A | 4 | Primary Net Control (linked to A Group) | DULLES K4IAD | Loudoun EOC | 147.330 + | 203.5 Hz | + 0.6 MHz | 203.5 Hz | FM Voice | Dulles Airport | 
A | 5 | Secondary Net Control (linked to A Group) | WA3KOK – NERA Repeater | Loudoun EOC | 447.775- | 107.2 Hz | - 5.0 MHz | 107.2 Hz | FM Voice | Bull Run Mountain, Antioch, VA (use isTBD) | 
B | 6 | Secondary Net Control (linked to B Group) | WA4TXE – Leesburg Linked | Loudoun EOC | 146.700- | 77.0 Hz | – 0.6 MHz | 77.0 Hz | FM Voice | • use if Primary Net is not available • use for specialized discussions | 
B | 7 | Secondary Net Control (linked to B Group) | WA4TXE - Purcellville Linked | Loudoun EOC | 146.850- | 77.0 Hz | – 0.6 MHz | 77.0 Hz | FM Voice | • use if Primary Net is not available • use for specialized discussions | 
C | 8 | Simplex 1 | Loudon ARES Simplex 1 | Loudoun EOC and all stations as needed | 147.48 | 103.5 (If needed) | 147.48 | 103.5 (If needed) | FM Voice | • use if Primary Net is not available • use for specialized discussions | 
C | 9 | Simplex 2 | Loudon ARES Simplex 2 | Loudoun EOC and all stations as needed | 146.40 | 103.5 (If needed) | 146.40 | 103.5 (If needed) | FM Voice | • use if Primary Net is not available • use for specialized discussions | 
D | 10 | WinLink Data | Simplex | All Stations as capability allows | 145.73 |  | 145.73 |  | WinLink Digital | Familiarization, new capability testing | 
E | 11 | WinLink Data | Simplex | Interested stations | HF From WinLink List |  |  |  | WinLink Digital | Familiarization, new capability testing, Run HF to out of area WinLink node to send files & email through Internet | 
F | 12 | APRS Location Tracking | Simplex | All Stations | 144.39 |  | 144.39 |  | APRS | See table on location beacon station assignments | 
G | 13 | NVREGN/Northern Virginia Regional Operations and Coordination | Simplex | Loudoun EOC | 146.910 - |  | – 0.6 MHz | 77.0 Hz | FM Voice |  | 
H | 14 | MDREGN/Maryland Regional Operation and Coordination | Simplex | Loudoun EOC | 147.105 + |  | + 0.6 MHz |  | FM Voice |  | 
I | 15 | ARC-CHP/Red Cross Chapter-to-Chapter communications | Simplex | Loudoun EOC | 146.535 |  |  |  | FM Voice |  | 
J | 16 | KT4ER/Bull Run Mountain |  | Loudoun EOC | 448.325- |  | - 5.0 MHz | 100.0 Hz | FM Voice | Additional backup if needed (not coordinated for this exercise) | 
5. Special Instructions: * WA4TXE – General Loudoun coverage - Non-standard split - receive the output from the Leesburg 146.700 repeater and transmit to the Purcellville repeater using it’s input frequency of 146.250 -- 146.70 RX/146.25 TX |  |  |  |  |  |  |  |  |  |  | 

## Slide 9: Master Scenario Events List (MSEL) Summary (in work)
Use Virginia SET Plan as starting point and add detail
Time-based listing of activities to be conducted during the event

## Slide 10: Exercise Metrics
Use ARRL’s metrics and report participation to ARRL – need to work

## Slide 11: Actions
Have Scott Morse (and others) review this draft exercise pland
Post SET plan briefing on LARES web site after final review
Set up Signup Genius positions to get volunteers
  Will take volunteers now
Develop Master Scenario Events List (MSEL)
  Define start and end times for event
  Define fixed station locations to simulate shelters
  Define dispatch tasking & timeline for mobile operators
  Define times to inject simulated messages into comm networks
Need volunteer to define WinLink messages and forms to be used
Define pre-canned simulated messages to be sent by all stations
Define data collection needs for lessons learned and ARRL report development
Get LARG APRS position trackers
Distribute LARG APRS position trackers to operators
Define ARRL exercise metrics and possibly refine plan
Distribute final Event Plan and Comm Plan/MSEL to participants
Recommend participants take FEMA & ARRL training courses (counts for ARRL scoring) nice to have but not required
Ask all participants to take pictures and record any observations & lessons learned – send to Doug KM4GC
More????