## Slide 1: 2024 Loudoun ARES Simulated Emergency Test (SET) Plan
Event Date: 5 October 2024
Event Time: 1000 to 1200 EDT
(1400 to 1600 Z)
Send questions and comments to:
Doug McNulty KM4GC
datacomsys@comcast.net

## Slide 2: Background
Background:
  Amateur Radio Emergency Service (ARES) consists of licensed amateurs who have voluntarily registered their qualifications and equipment, with their local ARES leadership, for communications duty in the public service when disaster strikes (from ARRL)
    includes training, preparation, organization, and guidelines
  The Simulated Emergency Test (SET) is one of the ARRL activities to exercise/practice emergency communications (EMCOMM)
    usually in early October
    Is conducted nation-wide and at the local level
    Is scenario based

## Slide 3: Purpose & Scope
Purpose of the Loudoun ARES SET for 2024:
  To kick start Loudoun ARES activities for EMCOMM training and
  To exercise a draft comm plan
  To introduce the use of text-based data transfer (most like type of support served agencies need in real world situations)
Scope: Conducted within Loudoun County using the Loudoun Emergency Operations Center (EMOC) to:
  Coordinate a limited number of fixed and mobile ham stations for the transfer of simulated emergency messages (similar to LARG support for bike events)
  Use linked repeater assets – for start of exercise
  Include a simulated fail over period to exercise simplex communications
  Include testing of WinLink to transfer email and standard forms
  May or may not include connections to EMCOMM interfaces outside of the county such as the National Traffic System (NTS)

## Slide 4: Scenario (adapted from the Virginia ARES 2024 SET Plan)
Type of Emergency: This exercise will use the scenario of a Virginia-wide winter storm, with some widespread power outages, many smaller localized outages, and reduced transportation due to snow, ice, downed trees, flooding, etc.
Loudoun ARES (LARES) is asked to provide auxiliary communications for Loudoun County emergency services organizations for set up and operation of shelters, warming stations, food distribution facilities including Loudoun Inova Hospital’s support for the simulated emergency

## Slide 5: Loudon ARES Connectivity Concept
Inova Loudoun Hospital ARES Station
Simulated Mobile / Shelters / Food Distro or Other Supported Agency locations
Inova Loudoun Hospital Staff POC
EMOC LARES Command Post
Net Control
Dispatch Moble Stations
External Interfaces to
supported Agencies
Co-Located with Loudoun EOC
Directed Net (Primary)
Direct Message Exchange to hospital using secondary net
Directed Net (Primary)
= primarily HF digital
= primarily VHF/UHF FM voice
TBD
Peer-to-Peer Winlink (TBD)

## Slide 6: Planned Stations/Positions (1 of 4)
Simulated shelters supported by fixed stations
  VHF/UHF for in-county comms to net control
  HF for NTS welfare messages (depending on operator capabilities)
Two types of fixed stations
  Operators with portable or mobile VHF/UHF FM capability to operate from designated locations within the county
  Operators participating from their home (or other) locations that have VHF/UHF FM capability.
Optional additional HF WinLink capability is encouraged but not required.
  Simulated traffic to handle:
    number of injured, medical care needed, supplies needed
    welfare messages to relatives
    Both voice and Winlink (depending on operator capabilities)
  Adjust number of stations depending on number of volunteers

## Slide 7: Planned Stations/Positions (2 of 4)
Mobile stations
  VHF/UHF FM for in-county comms
  Rovers to report status of various things such as bridges, power stations, road conditions around the county, and to transport supplies as dispatched by Net Control
  Adjust number of stations depending on number of volunteers

## Slide 8: Planned Stations/Positions (3 of 4)
Loudoun Inova Hospital ARES Station
  VHF/UHF for in-county comms to Loudoun Emergency Operations Center and shelters as needed
  Potential external Winlink connection
  Operators:
    Dan Sloan K4BCR
    Marc Spaziano N1BED
  Simulated traffic to handle:
    number of injured, medical care needed, supplies needed
    FM Voice

## Slide 9: Planned Stations/Positions (4 of 4)
Loudoun Emergency Operations Center (EOC)
  Net control for comm nets (in-county comms)
  Execute MSEL
  External interface to Red Cross, and other supported agencies, Virginia Section ARES (may not be used for this exercise)
  Operators:
    Scott Morse WB6EFW
    Ron White KQ4IBI
    Steve Radloff N4RAF
    Doug McNulty KM4GC
  Simulated Traffic to handle:
    Primary interface with county emergency personnel
    number of injured, medical care needed, supplies needed
    welfare messages to relatives (both in and out of county?)
    Dispatch mobile stations
    Both voice and Winlink

## Slide 10: Candidate Simulated Loudoun County Shelter Locations for Portable Stations
Attempt to locate portable stations around the county to assess communications coverage
Up to individual operators to select specific location if operating portable station – please specify location at sign up or if changed for event
Following locations are just ideas
  Leesburg - Ida Lee Park
  Ashburn/Brambelton – Stream Valley
  Purcellville/Round Hill – Franklin Park
  Lovettsville – Lovettsville Community Park
  South Riding – Mink Meadows Pond Park
  Philomont – Philomont Community Center
  Middleburg – Glenwood Park
  Sterling – Claude Moore

## Slide 11: Comm Plan
Operators need to include the words “EXERCISE EXERECISE EXERCISE” at the start of all messages – both verbally and text-based
  Not needed before every transmission
    such as requesting permission from net control to contact another station to pass data or that a station will be off line for a few minutes
  Needed when providing simulated message data or reporting simulated status information
See following page for frequencies and nets to be used
For Zone/group B, but we are not sure yet if we can link WA3KOK to one of the WA4TXE repeaters yet - in work
  By linked we mean what is received by one repeater is transmitted out on the other repeater(s)
Operators can use which ever repeater provides the best connection within the zone/group for desired net to be used
Operators are requested to load all frequencies and repeater access information in their radio memories before the exercise to be able to rapidly QSY (change frequencies/repeaters)
  shifting to different nets will be part of the exercise

## Slide 12: INCIDENT RADIO COMMUNICATIONS PLAN (ICS 205) – DRAFT as of 14:00 24 Sep 24 not final
Zone Grp. | Ch # | Function | Channel Name/Trunked Radio Sys Grp | Assignment | RX Freq N or W | RX Tone/NAC | TX Freq N or W | TX Tone/NAC | Mode (A, D, or M) | Remarks | 
A | 1 | Primary Net Control | LOUDOUN ARES WB6EFW VHF FM | Loudoun EOC and all stations | 145.185- | 103.5 Hz | – 0.6 MHz | 103.5 Hz | FM Voice | Repeater located at Inova Hospital Lansdown | 
B | 2 | Secondary Net Control (linked to B Group TBR) | WA3KOK | Loudoun EOC and all stations | 444.75+ | 100 Hz | +5 MHz | 100 Hz | FM Voice | • use if Primary Net is not available • use for specialized discussions | 
B | 3 | Secondary Net Control (linked to B Group) | WA4TXE – Leesburg Linked | Loudoun EOC and all stations | 146.700- | 77.0 Hz | – 0.6 MHz | 77.0 Hz | FM Voice | • use if Primary Net is not available • use for specialized discussions | 
B | 4 | Secondary Net Control (linked to B Group) | WA4TXE – Purcellville Lnked | Loudoun EOC and all stations | 146.850- | 77.0 Hz | 146.1 MHz | 77.0 Hz | FM Voice | • use if Primary Net is not available • use for specialized discussions | 
C | 5 | Simplex 1 | Loudon ARES Simplex 1 | Loudoun EOC and all stations | 147.48 | 103.5 (If needed) | 147.48 | 103.5 (If needed) | FM Voice | • use if Primary Net is not avail • use for specialized discussions | 
C | 6 | Simplex 2 | Loudon ARES Simplex 2 | Loudoun EOC and all stations | 146.40 | 103.5 (If needed) | 146.40 | 103.5 (If needed) | FM Voice | • use if Primary Net is not available • use for specialized discussions | 
D | 7 | WinLink Data | Simplex | Interested stations | HF From WinLink List | n/a | Simplex | n/a | WinLink Digital | Familiarization, new capability testing, Run HF to out of area WinLink node | 
D | 98 | WinLink Data | Simplex N2LEE Reston | Interested stations | 145.73 | n/a | 145.73 | n/a | WinLink Digital | Familiarization, new capability test | 
D | 9 | WinLink Data | Simplex WM3M Rockville | Interested stations | 145.090 | n/a | 145.090 | n/a | WinLink Digital | Familiarization, new capability test | 
D | 10 | WinLink Data | Simplex N3HYM Frederick | Interested stations | 145.090 | n/a | 145.090 | n/a | WinLink Digital | Familiarization, new capability test | 
D | 11 | WinLink Data | Simplex KF3AK Hampstead, MD | Interested stations | 145.770 | n/a | 145.770 | n/a | WinLink Digital | Familiarization, new capability test | 
D | 12 | WinLink Data | Simplex NT8B Falls Church | Interested stations | 145.750 | n/a | 145.750 | n/a | WinLink Digital | Familiarization, new capability test | 
E | 13 | APRS Location Tracking | Simplex | Interested stations | 144.39 | n/a | 144.39 | n/a | APRS | See table on beacon station ssignments | 
F | 14 | NVREGN/Northern Virginia Regional Ops and Coord | NV4FM Tysons | Loudoun EOC | 146.910 - | 77.0 Hz | – 0.6 MHz | 77.0 Hz | FM Voice | Monitor | 
F | 15 | MDREGN/Maryland Regional Ops and Coord |  | Loudoun EOC | 147.105 + |  | + 0.6 MHz |  | FM Voice | Monitor | 
F | 16 | ARC-CHP/Red Cross Chapter-to-Chapter comms | Simplex | Loudoun EOC | 146.535 |  |  |  | FM Voice | Monitor | 
F | 17 | SkyWarn & NTS | BLUEMONT N3JLT | Loudoun EOC | 147.300+ | 146.2 Hz | + 0.6 MHz | 146.2 Hz | FM Voice | Monitor, Send message to NTS (TBD) | 

## Slide 13: Master Scenario Events List (MSEL) Summary (in work)
Use Virginia SET Plan as starting point and add detail
Time-based listing of activities to be conducted during the event
Mobile unit
  gets stuck and requests support
  Mobile unit reports road blockages due to blowing snow
  reports stranded motorist who requires medical assistance
Shelter reports
  Head count
  Needs food, maybe a certain type for a person at the shelter
  Reports medical emergency
General
  Cell service near one shelter / food distro site is off line – they can’t get ahold of anybody – LCARES becomes comm path back to EMOC
Food Distro
  Pass requirement from Shelters for food
  Provides status of stock for distribution

## Slide 14: Items Planned to be Issued to Operators Prior to SET
Master Scenario Event List (MESL) (time-based listing of activities)
Communications plan with station tactical call signs (such as “Shelter 1” or “Mobile 1”) and planned frequencies to be used
Pre-defined messages for your station to (under net control direction and as called for in the MESL):
  Pass to the addressed recipient station if in direct contact to the recipient site
  Pass for relay to another station if not in direct contact with the addressed recipient station
  Receive and acknowledge receipt of messages addressed to you
APRS Location Beacon (priority will be givento mobile and portable stations until we run out) – need to be returned
A survey questionnaire - so we can conduct a post-event evaluation

## Slide 15: Exercise Metrics
Use ARRL’s metrics and report participation to ARRL – need to work

## Slide 16: Actions
Have Scott Morse (and others) review this draft exercise plan
Post SET plan briefing on LARES web site after final review
Set up Signup Genius positions to get volunteers
  Will take volunteers now
Develop Master Scenario Events List (MSEL)
  Define start and end times for event
  Define fixed station locations to simulate shelters
  Define dispatch tasking & timeline for mobile operators
  Define times to inject simulated messages into comm networks
Make table of stations, operators, call signs, and APRS location beacons
Define WinLink messages and forms to be used
Define pre-canned simulated messages to be sent by all stations
Define data collection needs for lessons learned and ARRL report development
Get LARG APRS position trackers
Distribute LARG APRS position trackers to operators
Define ARRL exercise metrics and possibly refine plan
Distribute final Event Plan and Comm Plan/MSEL to participants
Recommend participants take FEMA & ARRL training courses (counts for ARRL scoring) nice to have but not required
Ask all participants to take pictures and record any observations & lessons learned – send to Doug KM4GC