## Slide 1: ARRL SET Exercise
Doug, KM4GC

## Slide 2: 2025 Loudoun ARES Simulated Emergency Test (SET) Plan
Briefing to LARG meeting 20 September 2025
Event Date: 4 October 2025
Event Time: 1000 to 1200 EDT
(1400 to 1600 Z)
Send questions and comments to:
Doug McNulty KM4GC
datacomsys@comcast.net

## Slide 3: Background
The Amateur Radio Emergency Service (ARES) consists of ham radio operators who volunteer to provide communications services when disaster strikes.
The Simulated Emergency Test (SET) is a training activity to help ham radio operators hone operational skills and refine radio station configurations to provide emergency communications services when and where needed.

## Slide 4: Scenario LCARS SET 2025
An major hurricane with several tornados has forced many county residents to relocate from their destroyed homes to county-provided shelters.
Primary communications used by county officials including cell phone service is mostly off-line and intermittent at best.
Loudoun County ARES (LCARES) has been asked to provide auxiliary communications between the Loudoun County Emergency Operations Center (EOC) and various shelters

## Slide 5: Loudon ARES Connectivity Concept
Inova Loudoun Hospital LCARES Station
LCARES Portable Stations – Relay Messages between EMOC and local Shelter Staff
Inova Loudoun Hospital Staff POC
EOC LCARES Station
Net Control
Co-Located with Loudoun EOC
Relay messages for Loudoun County Emergency Services Groups
= RF voice/WINLINK
Liaison LCARES Station
Interfaces with external amateur emergency networks (VHF/UHF/HF)
Not Co-Located with Loudoun EOC
Backup to Net EOC Control
Portable Station
= Local intra-building interface

## Slide 6: Exercise Approach (1 of 2)
Participating hams will be deployed to various simulated shelter locations to set up a portable station
Type of message transfer will primarily consist of FM voice RF traffic
Depending on the capabilities of participating stations some WINLINK-based message passing may be conducted
Pre-canned messages will be distributed to participants prior to the event. Messages will indicate when they should be transmitted.
Participants will send and receive messages to/from Net Control in accordance with the time-based MSEL (at Net Control)

## Slide 7: Exercise Approach (2 of 2)
The LARG frequency plan will be used for the various nets
  Commonality for loading frequencies in rigs between LARG events
  Will call out channel numbers to use if changing
  Linked channels 1 and 2 will be used for primary net operations and initial station check in
  May be augmented for WINLINK and external interfaces (if included in the exercise)
Participants will be asked to take pictures and record any observations & lessons learned – send to Doug KM4GC at end of exercise

## Slide 8: Planned Stations for Exercise
Simulated shelter locations
  may include some Loudoun County high school and other location parking lots – but not finalized, in-county coordination is in work
  see candidate list on following pages
  Will ask operators for preferred set up location
  Final location assignments will be distributed prior to event – assignments are not binding – see next page
Loudoun Emergency Operations Center (EOC)
  Net control
  Execute MSEL
Liaison Station – TBD if we will have resources
Loudoun Inova Hospital ARES Station – TBD if we will have resources
Need operators – use sign up sheet or email me

## Slide 9: Rain (or Shine) on Day of Exercise
Field deployment location is up to each operator (rain or shine)
  Can deploy to assigned location as originally planned
  Can deploy to a different location as desired such as a park that has a picnic shelter at a nearby park
  Can operate from vehicle at a chosen site by operator
  Can operate from home
Please let Net Control know your location at check in

## Slide 10: Potential Simulated Exercise Shelter Locations - Designated County Shelter Sites - TBD
County High Schools:
  Briar Woods
  Broad Run
  Dominion
  Freedom
  Heritage
  Independence
  John Champe
  Lightridge
  Loudoun County
  Loudoun Valley
  Park View
  Potomac Falls
  Riverside
  Rock Ridge
  Stone Bridge
  Tuscarora
  Woodgrove
Rec centers/middle school :
  Claude Moore Rec Center
  Dulles South – Rec Center
  Dulles South – Senior Center
  Harmony Intermediate School

## Slide 11: Potential Simulated Exercise Shelter Locations - TBD
Following locations are additional operating location ideas – but are not designated as county shelter locations
  Leesburg - Ida Lee Park
  Ashburn/Brambelton – Stream Valley
  Purcellville/Round Hill – Franklin Park
  Lovettsville – Lovettsville Community Park
  South Riding – Mink Meadows Pond Park
  Philomont – Philomont Community Center
  Middleburg – Glenwood Park
  Sterling – Claude Moore Park